## Slide 1: Annual Utility Coordination Meeting
Spring 2022

## Slide 2: Agenda
Introductions / Information Sharing
Sound Transit Lynnwood Link Extension Project Update
Surface Water Utility Reminders
City of Shoreline Projects (2022 and beyond)
Utility Providers Description of Upcoming Projects
Open Discussion / Feedback

## Slide 3: Lynnwood Link Extension
Project Limits: Periodic closures at all Interchanges 5th Ave NE @ NE 145th St to NE 148th St NE 195th St @ I-5 to 10th Ave NE NE 189th St. @ I-5 to 8th Ave NE and 8th Ave NE from NE 189th St. to NE 185th St 5th Ave NE @ NE 182nd Ct to NE 185th St 1st Ave NE @ NE 170th St to NE 174th St 1st Ave NE @ NE 159th St to NE 161st St
Scope: Utility relocation/modification Roadway reconstruction of 5th, 8th, 1st Ave NE and NE 195th and 185th St. Guideway, Stations, Garages, and Transit Loops
Status: In construction
Construction Window: 2019-2023
Ginger Ferguson, PE
ST L200 Construction Manager
(206) 398-5138
ginger.ferguson@soundtransit.org
Soundtransit.org/lynnwoodlink
Juniper Nammi, AICP
City of Shoreline Light Rail PM
(206) 801-2525
jnammi@shorelinewa.gov

## Slide 4: Surface Water Utility – Dan Sinkovich
Surface Water Utility Reminders
  Discharges of Potable Water to City Right-of-Way
  Staging of Utility Materials in Stormwater Ditches
  Utility Cross Bore Removals Continue

## Slide 5
If you have questions, contact Stefan Grozev at (206) 801-2453 or sgrozev@shorelinewa.gov

## Slide 8: City of Shoreline 2022-2027 CIP

## Slide 9: Capital Improvement Map, page 2

## Slide 10: Stormwater Pipe Repair and Replacement Program
Project Limits: Citywide.
Scope: To repair damaged stormwater pipes, prioritized based on severity of damage and importance of pipe. Combination of CIPP and open-cut repairs. Multiple sites batched into one project.
Status: Design for 2022 construction (open-cut)
Construction Window: Summer 2022
Utility Coordination Needed: No relocations anticipated.
Lea Bonebrake, PM
(206) 801-2475
lbonebrake@shorelinewa.gov
Stormwater Pipe Repair and Replaement Program

## Slide 11: Surface Water Small Drainage Projects
Project Limits: Citywide.
Scope: Program to fix small public drainage issues. Construction typically includes installation of catch basins, pipes, berms and other small improvements within the public right-of-way. Multiple sites batched into one project.
Status: Design for 2022 construction
Construction Window: Summer 2022
Utility Coordination Needed: No relocations anticipated.
Lea Bonebrake, PM
(206) 801-2475
lbonebrake@shorelinewa.gov
Surface Water Small Drainage Projects

## Slide 12: Lower Storm Creek Erosion Management Project
Project Limits: Lower end of Storm Creek (west of 17th Pl NW)
Scope: Construction to address severe down-cutting erosion of the Storm Creek channel west of 17th Pl NW
Status: Preliminary Design
Construction Window: Summer 2023
Utility Coordination Needed: Wastewater
Lea Bonebrake, PM
(206) 801-2475
lbonebrake@shorelinewa.gov
Website coming soon

## Slide 13: N 148th St Non-Motorized Bridge Project
Project Limits: N 148th Street & I-5
Scope: Construct a new ped/bike bridge over I-5 at N 148th Street to provide a connection between 1st Ave NE and the new Shoreline South/148th Station.
Status: 90% Design
Construction Window: Phase 1: Summer 2022-Spring 2023 Phase 2: TBD
Utility Coordination Needed: (Phase 1) Wastewater and SCL (Phase 2) SCL and communication relocations.
Lea Bonebrake, PM
(206) 801-2475
lbonebrake@shorelinewa.gov
N 148th Non-Motorized BridgeProject

## Slide 14: 1st Ave NE Sidewalks (N 145th to N 155th)
Project Limits: 1st Avenue NE between N 145th Street and N 155th Street.
Scope: Construct sidewalk along 1st Ave NE.
Status: Contracting / Preliminary Design
Construction Window: Spring/Summer 2023
Utility Coordination Needed: Utility adjustments and relocations.
Leif Johansen, PM
(206) 801-2489
ljohansen@shorelinewa.gov
1st Avenue NE Sidewalks (145th- 155th)

## Slide 15: N 175th Street (Stone Avenue N to I-5)
Project Limits: N 175th Street between Stone Avenue N and I-5
Scope: Reconstruct roadway. New signal at Meridian/175th St. Provide pedestrian and bicycle facilities. Utility undergrounding. Water and sewer relocation/upgrades are expected
Status: 50% Design, Utility Coordination
Construction Window: 2025 and beyond
Utility Coordination Needed: SCL, SPU, Comcast, Ziply, PSE, RWD
Leif Johansen, PM
(206) 801-2489
ljohansen@shorelinewa.gov
N 175 Street Corridor Improvements Project

## Slide 16: Meridian Avenue Safety Improvements
Project Limits: Meridian Avenue between N 155th Street and N 175th Street.
Scope: Rechannelize Meridian Avenue. Install RRFBs at N 163rd Street and N 17oth Street.
Status: Contracting/Preliminary Design
Construction Window: Spring/Summer 2023
Utility Coordination Needed: Power service for RRFB and utility adjustments (WA and telecom.)
Leif Johansen, PM
(206) 801-2489
ljohansen@shorelinewa.gov
Meridian Avenue Safety Improvements

## Slide 17: 5th Ave NE (165th to 175th) Sidewalk Rehabilitation
Project Limits: 5th Ave NE between NE 165th St and NE 175th St.
Scope: Remove barriers to pedestrian mobility. Sidewalk and ramp spot repairs.
Status: Preliminary design
Construction Window: Spring/Summer 2023
Utility Coordination Needed: Utility adjustments
Leif Johansen, PM
(206) 801-2489
ljohansen@shorelinewa.gov
Website coming soon

## Slide 18: New Sidewalks, 5th Ave NE: 175th to 182nd
Project Limits: 5th Avenue NE from N 175th Street to near 182nd Court.
Scope: Construct new concrete sidewalks on the both sides of 5th Avenue NE.
Status: Construction
Construction Window: April - September 2022
Utility Coordination Needed: SCL power pole relocation, North City hydrant/valve/meter relocations, PSE relocation
Laura Reiter, PM
(206) 801-2475
lreiter@shorelinewa.gov
New Sidewalks: 5th Avenue NE (175th St to 182nd Ct)

## Slide 19: New Sidewalks, 20th Ave NW: 190th to 195th
Project Limits: 20th Avenue NE from NW 190th – NW 195th Street
Scope: Construct new concrete sidewalks on the west side of 20th Avenue NW.
Status: Design
Construction Window: September – November 2022
Utility Coordination Needed: SCL power pole relocation, SPU meter relocations, PSE gas services
Laura Reiter, PM
(206) 801-2475
lreiter@shorelinewa.gov
New Sidewalks: 20th Ave NW (190th St to 195th St)

## Slide 20: New Sidewalks, Westminster Way (145th – 153rd)
Project Limits: Westminster Way from 145th to 153rd St.
Scope: Construct new concrete sidewalks on the one side of Westminster Way.
Status: Pre-Design
Construction Window: April - September 2023
Utility Coordination Needed: SCL power pole relocation, SPU hydrant/valve/meter relocations, PSE relocation
Laura Reiter, PM
(206) 801-2475
lreiter@shorelinewa.gov
Website coming soon

## Slide 21: Ridgecrest Safe Routes to School
Project Limits: NE 165th Street between 10th Avenue NE and 15th Avenue NE.
Scope: Installing two new school speed zone flashers and speed feedback signs, curb extensions, and crosswalk signage.
Status: Design
Construction Window: June / August 2022
Utility Coordination Needed: SCL service
Laura Reiter, PM
(206) 801-2457
lreiter@shorelinewa.gov
Ridgecrest Safe Routes to School

## Slide 22: Hidden Lake Dam Removal
Project Limits: Hidden Lake within Shoreview Park and the adjacent NW Innis Arden Way.
Scope: Removal of Hidden Lake Dam, restoration of Boeing Creek through the existing lake, and replacement of the culverts under NW Innis Arden Wy.
Status: Design
Construction Window: Phase 1: May/September 2022 Phase 2: May/September 2024
Utility Coordination Needed: None for Phase 1; SPU/Comcast for Phase 2
Laura Reiter, PM
(206) 801-2457
lreiter@shorelinewa.gov
Hidden Lake Dam Removal

## Slide 23: NE 148th Street Infiltration Facilities
Project Limits: NE 148th Street from 12th Ave NE to 15th Avenue NE.
Scope: Construction of underground infiltration facilities.
Status: Construction
Construction Window: April / May 2022
Utility Coordination Needed: North City Water District service/meter relocation
Laura Reiter, PM
(206) 801-2457
lreiter@shorelinewa.gov
NE 148th Infiltration Facilities

## Slide 24: City Maintenance Facility (Ballinger)
Project Limits: Brightwater Maintenance Facility Site 20031 Ballinger Way NE.
Scope: New city maintenance facility for vehicle fueling and washing, snow and ice removal, decant facility, and site improvements.
Status: Design
Construction Window: April 2022 – January 2023
Utility Coordination Needed: Utility connections approved thru site development permit.
Zachary Evans, PM
(206) 801-2428
zevans@shoreline.wa.gov
City Maintenance Facility (Ballinger)

## Slide 25: 15th Ave NE Sidewalk Rehabilitation
Project Limits: 15th Ave NE sidewalks from NE 155th St to NE 175th St
Scope: Repair damaged sidewalk panels, install new ADA ramps and repair other minor barriers to ADA access as funding allows.
Status: Design
Construction Window: July 2022 – December 2022
Utility Coordination Needed: Potential relocation of water meters to amenity zone.
Zachary Evans, PM
(206) 801-2428
zevans@shoreline.wa.gov
15th Ave NE Sidewalk Rehabilitation

## Slide 26: Richmond Beach Midblock Crossing and Citywide Rectangular Rapid Flashing Beacons (RRFB) and Radar Speed Signs (RSS)
Project Limits: Midblock crossing on NW Richmond Beach Road between 8th Ave NW and 3rd Ave NW. Multiple locations for RRFB and RSS. See vicinity map.
Scope: New midblock crossing with ADA ramps, refuge island, RRFBs and upgraded lighting. RRFB installation at 9-13 pedestrian crosswalks plus minor striping improvements. 3 RSSs locations.
Status: Design
Construction Window: Fall 2022- Winter 2023
Utility Coordination Needed: Potential impact to water meters at midblock crossing. Coordination with SCL on potential hardwire RRFBs.
Zachary Evans, PM
(206) 801-2428
zevans@shoreline.wa.gov
Richmond Beach Road Midblock Crossing

## Slide 27: Pump Station 26 Improvements Project
Project Limits: Pump Station 26 (18351 10th Ave NE)
Scope: Full replacement of existing pump station and detention pond at PS-26 and frontage improvements. Same construction contract as Miscellaneous Pump Stations project.
Status: Design
Construction Window: April 2022 – December 2022
Utility Coordination Needed: Power and water approved thru site development permit.
Zachary Evans, PM
(206) 801-2428
zevans@shoreline.wa.gov
Pump Station 26 Improvements Project

## Slide 28: Pump Station Miscellaneous Improvements
Project Limits: Minor improvements at 6 existing surface water pump stations. See vicinity map.
Scope: Minor pump station improvements such as adding SCADA, signage, safety grates, post mounts, etc. Same construction contract as PS-26.
Status: Preliminary Design
Construction Window: April 2022 – December 2022
Utility Coordination Needed: Minor electrical service upgrades, general coordination for minor trench work in the ROW.
Zachary Evans, PM
(206) 801-2428
zevans@shoreline.wa.gov
Pump Station – Miscellaneous Sites

## Slide 29: Annual Road Surface Maintenance
Project Limits: 2022 – 155th Overlay Midvale to I-5
Scope: 155th overlay – grind and overlay, ADA ramps to standard.
Status: 2022 155th overlay – in Design
Construction Window: 155th overlay – Summer 2022 – Spring 2023
Utility Coordination Needed: 155th overlay – complete utility work in advance of overlay
Kristin Terpstra, PM
(206) 391-3364
kterpstra@shorelinewa.gov
Annual Road Surface Maintenance Program

## Slide 30: Pavement Maintenance/Moratorium Map http://www.shorelinewa.gov/government/projects-initiatives/annual-road-surface-maintenance-program
Insert Map

## Slide 31: SR-523 (N/NE 145th Street), Aurora Avenue N to I-5
Project Limits: N 145th Street (Linden Avenue to I-5)
Scope: Widen 145th Street to accommodate design elements that will improve traffic operations, safety and mobility throughout the corridor.
Status: Design & ROW (Phase 1)
Construction Window: Phase 1 (I-5 to Corliss): 2023/2024 Phase 2 (Corliss to Wallingford): 2025/2026 Phase 3 (Wallingford to Linden): TBD
Utility Coordination Needed: SCL undergrounding approach & subarea service needs, SPU water & stormwater, JUT for communication
Cory Nau, PM
(206) 801-2325 cnau@shorelinewa.gov
145th Street Corridor Project

## Slide 32: SR 523(145th) and I-5 Interchange Project
Project Limits: SR 523 (NE 145th) 1st Avenue NE to 6th Avenue NE
Scope: Replace signalized intersections at I-5 Southbound and 5th Avenue NE with Roundabouts.
Status: Design (30%)
Construction Window: Fall 2022 through December 2023
Utility Coordination Needed: SCL power line relocation SPU water main relocation
Robert McGaughy, PM
rmcgaughey@shorelinewa.gov 145th & I5 Interchange Project

## Slide 33: SR 523(145th) and I-5 Interchange Project

## Slide 34: SR 523(145th) and I-5 Interchange Project
Placeholder for grading profile

## Slide 35: Ridgecrest 5 CIP Sanitary Sewer Replacement
Tucker Collins, PM
WWU Consultant Engineer
David Evans and Assoc., Inc.
(425) 586-9748
Tucker.Collins@deainc.com
Project Limits: Various locations, see vicinity map.
Scope: Construction of approx. 3,600 linear ft of 8-inch HDPE sanitary sewer main via pipe bursting; replacement of approx. 61 associated side sewers via pipe bursting; installation of approximately 100 associated clean outs; rehabilitation of approximately 20 associated manholes; surface restoration; ADA ramp replacement; asphalt grind and overlay; and pavement marking replacement.
Status: Post 90% COSH Plan and Spec review, 100% Bid Set in progress.
Construction Window: July 2022 – May 2023
Utility Coordination Needed: Overlays noted in red above, if other utility work is planned in overlay area in near future, may be beneficial to combine work